## Sheet1
[6 empty] | Hours | Out of scope | In scope | Invoice during out of contract
2014-02-01 |  |  | Out of scope
| 1607 | 2014-02-17 | RFL 1630 Patch red hat CCMTransfer | Robyn Douglas | Telmax21 Support | 1
| 1609 | 2014-02-18 | IBM informix WTK thin client need for red hat | Robyn Douglas | Telmax21 Support | 1 | 2
2014-06-01 |  |  | Out of scope - Investigation and preparation work for Telmax21 move to Red Hat Enterprise Linux 5.6
| 1702 | 2014-03-12 | Phone discussion quote and emails |  |  | 4
| 1703 | 2014-03-17 | Text menu replacement research |  |  | 4
| 1704 | 2014-06-04 | Work with Open Gear USA on terminal server modem dialing |  |  | 16 | -2
| 1705 | 2014-05-08 | Requirements |  |  | 4
| 1706 | 2014-03-07 | Security scans |  |  | 5 | 33
In-Scope work for RedHat Enterprise Linux 5.6 Telmax21 Migration
| 1702 | 2014-06-02 | VTJUN14 RHEL1 Eval Staus |  |  | 1
| 1702 | 2014-06-04 | VTJUN14 RHEL1 Eval Staus |  |  | 0.25
| 1702 | 2014-06-07 | VTJUN14 RHEL1 Disk Partitioning |  |  | 2.5
| 1702 | 2014-06-09 | VTJUN14 RHEL1 User/Data Copy/rsync for apps. & DB |  |  | 5
| 1702 | 2014-06-11 | VTJUN14 RHEL1 Integrated LDAP/PAM Authenication |  |  | 0.25
| 1702 | 2014-06-15 | VTJUN14 RHEL1 Integrated LDAP/PAM Authenication |  |  | 0.25
| 1702 | 2014-06-16 | VTJUN14 RHEL1 Integrated LDAP/PAM Authenication |  |  | 0.5
| 1702 | 2014-06-17 | VTJUN14 RHEL1 Integrated LDAP/PAM Authenication |  |  | 0.25
| 1702 | 2014-06-18 | VTJUN14 RHEL1 Integrated LDAP/PAM Authenication |  |  | 0.75
| 1702 | 2014-06-19 | VTJUN14 RHEL1 Integrated LDAP/PAM Authenication |  |  | 0.25 | 3 | 9
2014-07-01 |  |  | integrated auth
| Reference | Date | Task Description | Requested By | Product/Service Type | Daily Hours
| 1715 | 2014-07-22 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 0.25
| 1715 | 2014-07-23 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 0.75
| 1715 | 2014-07-24 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 0.25
| 1715 | 2014-07-25 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 0.25
| 1715 | 2014-07-28 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 0.5
| 1715 | 2014-07-29 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 0.5
| 1715 | 2014-07-30 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 0.5
NCR Summary Totals - integrated auth work
| NCR | Created | Description | Requested By | Type |  | Hours |  |  | this looks to be when we started deducting hours from the monthly reconciliation
| 1715 | 2014-07-17 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support |  | 3 |  | -3 | No longer under quote. Robyn requested it be placed under support times
2014-08-01 |  |  | out of scope
| 1715 | 2014-08-18 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 1
| 1715 | 2014-08-20 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 1
| 1715 | 2014-08-21 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 2
| 1715 | 2014-08-22 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 0.75
| 1715 | 2014-07-17 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support |  | 5
In-Scope Quote work
| Reference | Date | Task Description | Requested By | Product/Service Type | Daily Hours
| 1715 | 2014-08-06 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 2
| 1715 | 2014-08-13 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 1
| 1715 | 2014-08-16 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 1.75
| 1715 | 2014-08-17 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 1
| 1715 | 2014-08-18 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 2
| 1715 | 2014-08-19 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 2
| 1715 | 2014-08-20 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 2.75
| 1715 | 2014-08-21 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 0.5
| 1715 | 2014-08-23 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 3
| 1715 | 2014-08-24 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 2
NCR Summary Totals - In-Scope Quote work
| NCR | Created | Description | Requested By | Type | Daily | Hours
| 1715 | 2014-07-17 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support |  |  | 18 | -18 | No longer under quote. Robyn requested it be placed under support times
2014-09-01 |  |  | Out of scope
| 1715 | 2014-09-23 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 0.75
| 1715 | 2014-07-17 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 4.75 | 5
In-Scope Quote work
| Reference | Date | Task Description | Requested By | Product/Service Type | Daily Hours
| 1715 | 2014-09-05 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 0.5
| 1715 | 2014-09-24 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 2
| 1715 | 2014-09-25 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 3.5
| 1715 | 2014-09-26 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 3
| 1715 | 2014-09-28 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 0.25
| 1715 | 2014-09-30 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 1
NCR Summary Totals - In-Scope Quote work
| NCR | Created | Description | Requested By | Type | Daily | Hours
| 1715 | 2014-07-17 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support |  |  | 11 | -11 | No longer under quote. Robyn requested it be placed under support times
2014-10-01 |  |  | In-Scope Quote work
| Reference | Date | Task Description | Requested By | Product/Service Type | Daily Hours
| 1715 | 2014-11-08 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 1.5
| 1715 | 2014-11-17 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 0.25
| 1715 | 2014-11-26 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 0.5
NCR Summary Totals - In-Scope Quote work
| NCR | Created | Description | Requested By | Type | Daily | Hours
| 1715 | 2014-07-17 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support |  |  | 3
2014-11-01 |  |  | In-Scope Quote work
| Reference | Date | Task Description | Requested By | Product/Service Type | Daily Hours
| 1715 | 2014-11-08 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 1.5
| 1715 | 2014-11-17 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 0.25
| 1715 | 2014-11-26 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support | 0.5
NCR Summary Totals - In-Scope Quote work
| NCR | Created | Description | Requested By | Type | Daily | Hours
| 1715 | 2014-07-17 | Fw: rhel telmax21 eval status | Robyn Douglas | Telmax21 Support |  |  | 3
|  |  | Unrecorded work done on original In-scope Quote work, done while it was still under quote. Incl. scosh text menu replacement |  |  | 28 |  | 28
|  |  | Estimate for work remaing when Karl does his work on the PBIS |  |  | 8
Grand Total | [6 empty] | 49 | 72 | -32 | 89
0